## Sheet1
Project Name | Online Bus Ticket Booking .
Created by | Vikas Landge,Shubham Kadam,Paurnima Salve
Creation date | 25/04/2019
Reviewed by
Reviewed date
Risk ID | Risk | Risk Mitigation | Risk Monitoring | Risk Management
RS_001 | Project size may increase. | Keep the extra storage ready. | Clear the extra cache and duplicate files. | Increase the capacity of database.
RS_002 | Database may get crashed. | Take the backup every week . | Manage the load on the database regularly. | Take the last updated backup.
RS_003 | Electricity issue. | Keep the backup ready. | Do the regular checkups. | Use the backup.
RS_004 | Shortage in technical resource. | Keep the extra supplies ready. | Keep the track on available resources. | Use the extra suppliers.
RS_005 | Business risk with competitor. | Keep the project More user friendly for end user. | Keep checking the requirements of the end users. | Try to make the project more user friendly and efficient.
RS_006 | Issue in time management. | Keep the backup plan for extending the time. | Complete the daily work as mentioned in the plan. | Request for extention of time from the client.
RS_007 | Cost of project the may increase. | Keep the client informed that the cost may increase. | Use of resources should be in limit as mentioned in the plan. | Ask the client for the increase in the payment.
RS_008 | Compatibility of project with different platforms. | Keep the project for easy updates. | Keep Checking for the new platforms in the market. | Update the project to make compatible with new platforms.
RS_009 | Shortage in human resources. | Keep the employees trained if extra required. | Assign the work to the employees as planned. | Take the help of extra employees who are trained for it.